## Slide 1: LITTLE SPROUTS –NURTURING HEALTHY CHAMPS
Team 2:
1.Pavithra Kadri
2. Priyanka Reddy Kuta
3. Yashita Raga Saranam
4. Shamily Reddy Muddam
5. Teja Pavani Jyesta
6. Hemanth Sai Kumar Gaddam
7. Rohith Sureddi

## Slide 2: BACKGROUND: Pediatric obesity is a significant public health concern, affecting around 17% of children in the United States and contributing to serious medical conditions such as heart disease, type 2 diabetes, and psychosocial disorders ( Sanyaolu et.al, 2019).
About the Project
through a mobile application.
To combat pediatric obesity
To provide knowledge and tool to
parents and caregivers in order to
promote healthy habit in children .
To nurture healthy champions
In order to build a better and
happier future for children.

## Slide 3
Develop a mobile application that serves as a comprehensive tool for fighting childhood obesity. It includes incorporating features like a nutrition tracking, physical activity monitoring, and AI-powered user personalization.
The primary aim is to educate and support parents, caregivers, and educators in promoting healthy lifestyles among children. The app aims to reduce childhood obesity and its related health problems by giving the essential tools and information.
By targeting a key issue - childhood obesity - the app has the potential to have significant impacts in the public health area. Its features and outreach have the potential to change the landscape of children health and wellness.
Adopts primary and secondary preventive measures for pediatric obesity, focusing on health education and early intervention, with strict adherence to data privacy and child safety regulations.
The application will be available on both mobile and web-based platforms, ensuring wide accessibility. It will provide a user-friendly interface that is engaging for children and informative for adults, making it a versatile tool for users of all ages.

## Slide 4
Benefits and Features
Personalized Health Guidance: AI-driven guidance for child-specific nutrition and activity
Interactive Content: Engaging educational tools for children that promote healthy habits
Parental Support : Tools and advice for parents to nurture a healthy lifestyle in children
Comprehensive Tracking: Tracks children's diet and physical activities
Data Security: Ensures user data safety and privacy

## Slide 5: PROJECT INITIATION
TEAM FORMATION
PROJECT PLANNING
BACKGROUND RESEARCH
VISION, GOALS AND OBJECTIVES
STAKEHOLDER ASSESSMENT
PROJECT CHARTER
WORK BREAKDOWN STRUCTURE

## Slide 6: WORK BREAKDOWN STRUCTURE
PROJECT INITIATION
APPLICATION DEVELOPMENT
PROJECT MANAGEMENT AND OVERSIGHT
MONITORING AND EVALUATION
APPLICATION TESTING AND LAUNCH
11 Sep – 04 Oct 2023
05 Oct – 17 Nov 2023
18 Nov – 04 Dec 2023

## Slide 7: Timeline
Project Initiation
Planning Phase
Application Design
Application Development
Application Testing
Monitoring and Evaluating
Project Closure
11 Sep 2023
14 Sep 2023
25 Sep 2023
09 Oct 2023
16 Nov 2023
01 Dec 2023
08 Dec 2023

## Slide 8: Budget planning

## Slide 9: Budget planning

## Slide 10
Stakeholder analysis:
Identified key stake holders (Parents, Health professionals and Developers)
Explained their interests, expectations and communication preferences
Communication objectives:
Informed parents about the app, educated on healthy habits, and created engagement.
Communication Channels:
App notifications, emails, social media
Monitoring and Evaluation:
Identified key performance indicators (KPIs) for success
COMMUNICATION PLAN

## Slide 11
Risk Identification:
Identified technical issues, user adoption challenges, data privacy concerns
Risk Analysis:
Assessed the likelihood and impact of each identified risk
Used a risk matrix or similar tool to visualize the analysis.
Risk Mitigation Strategies:
Presented strategies to mitigate or reduce the impact of identified risks.
Provided specific actions or measures for each risk.
RISK ASSESSMENT PLAN
Risk Monitoring:
Outlined the process for ongoing risk monitoring.
Discussed how frequently risks will be reassessed.
Communication of Risks:
Emphasized transparency and timely communication to stake holders.
Reporting Structure:
Identified who is responsible for overseeing risk-related activities.
Emphasized the iterative nature of risk management and continuous improvement been updated throughout the project.

## Slide 12
PROJECT EXECUTION
Mobile app design:
In the initial project phase, we prioritize creating a user-friendly and engaging mobile app through collaborative design sessions. We employ iterative processes, including wireframing and mockups, with continuous feedback loops to refine the app's structure. Our focus is on deliberate visual choices for consistency, brand recognition, and an intuitive user experience, ensuring appeal to our target audience.
Developing Mobile Application:
In the development phase, we prioritize building a robust mobile application with a modern and responsive front-end using contemporary frameworks. Simultaneously, the back-end focuses on a scalable database structure and efficient server-side logic. Integration of key features like nutrition monitoring, activity tracking, and AI-driven recommendations is coupled with rigorous testing, ensuring early issue identification and optimization for enhanced performance.
Mobile Application Testing:
Testing is a crucial phase in ensuring our mobile application's success. We follow a comprehensive strategy, beginning with unit testing to thoroughly check individual components and functions.
Next is integration testing, where we assess how different components interact seamlessly.
Real-world scenarios come into play during User Acceptance Testing (UAT), where a select user group provides valuable feedback, refining the overall user experience.
Lastly, performance testing evaluates scalability and responsiveness, enabling us to optimize the app for speed and efficiency. This thorough testing approach ensures our application is functional, user-friendly, and performs optimally.

## Slide 13
Launch preparation:
We create compelling marketing materials like videos, graphics, and social media content to build anticipation among our target audience.
Strategic social media campaigns and collaborations with influencers in health and parenting spaces help raise awareness and attract potential users.
Ensuring compliance with app store guidelines, submitting the app for review, and conducting pre-launch checks are vital steps to identify and address any issues that could impact performance.
Post launch monitoring:
Post-launch monitoring is a pivotal phase to ensure the sustained success of our mobile application. Through the implementation of app analytics, we meticulously track user behavior, engagement metrics, and key performance indicators.
Scheduled regular updates are part of our commitment to addressing bugs, introducing new features, and continually enhancing the app's functionality based on valuable user feedback and evolving needs.
In conclusion, our project has seamlessly progressed through the critical phases of design, development, testing, and launch preparation. With a steadfast commitment to a user-focused approach, our collaborative efforts have resulted in the creation of a mobile application designed to positively impact children's health.

## Slide 14
MONITORING & CONTROLLING
Little Sprouts - Nurturing Healthy Champs Application.
www.projectpractical.com

## Slide 15
Insert or Drag and Drop your Photo Here
Comprehensive Monitoring Tools: Utilized user engagement analytics and feedback mechanisms for tracking app performance and user satisfaction, enabling prompt identification and resolution of any deviations from the project plan.
Adaptive Control Mechanisms: Implemented regular team meetings and app updates based on user feedback, constantly refining strategies in response to health informatics trends and user behavior to maintain app quality and effectiveness.
Alignment with Goals and Objectives: Focused on ensuring the 'Little Sprouts' project aligns with its primary goals, particularly in impacting pediatric obesity.

## Slide 16
Adherence Trend Analysis: Monitoring and analyzing trends and patterns in user interaction with the app, especially in terms of adherence to recommended health practices and routines, to understand the underlying reasons for any deviations or non-compliance.
Feedback and Complaints Resolution: Assigning a dedicated team member to systematically track and respond to user feedback and complaints, developing strategies to address each issue which may include software modifications, additional user support, or targeted training programs.
Data Entry Standards and Accuracy: Implementing rigorous standards for data entry in the Little Sprouts app, including specific categories of information, frequency of entry, and data format, to ensure consistent and accurate submission of health data by users.

## Slide 17
PROJECT CLOSURE
Little Sprouts - Nurturing Healthy Champs Application.
www.ittoolkit.com

## Slide 18
Project Closure and Success Rate:
Impressive User Adoption: We saw a high number of downloads and active users, which was truly encouraging.
Behavioral Shift in Children: Noticed marked improvements in children's eating and activity habits, a core goal of our project.
Heartening Parental Feedback: Received overwhelmingly positive feedback from parents, affirming the app's impact and ease of use.
Engaging and Educative Approach: Proud of how effectively the app engaged children and provided useful insights to parents.

## Slide 19
Challenges Overcome:
AI Integration Journey: Faced and overcame significant challenges in embedding complex AI for personalized health advice.
Collaborative Learning: Learned immensely through extensive research and collaboration with health informatics experts.
Prioritizing Data Security: Took on the challenge of ensuring data security and privacy, a critical aspect given the sensitive nature of children's health data.

## Slide 20
Anticipating Future Problems and Solutions:
Keeping Engagement Alive: Aim to regularly refresh the app with new features and content to keep up with health trends.
Building a Supportive Community: Excited to create a space for parents to share experiences, enhancing the app's community feel.
Embracing Tech Innovations: Eager to explore advanced technologies like machine learning and augmented reality for more interactive experiences.

## Slide 21
CONCLUSION:
Our 'Little Sprouts' app has been a remarkable success, gaining widespread acceptance and positively influencing children's health behaviors, a testament to the practical application of our academic studies in health informatics.
While we've navigated through numerous challenges and enhanced our skill set, particularly in AI and data security, we're already identifying potential future obstacles. We're committed to addressing these proactively to maintain the app's effectiveness.
As we look ahead, we're hopeful that 'Little Sprouts app' will continue to make a significant difference in the lives of many children and parents, helping them lead healthier lives through informed choices and habits.

## Slide 22
Thank You
thedigitalprojectmanager.com